## Prod.Backlog
Product Backlog
EPIC ID | EPIC Name | User Story ID | User Story | Acceptance criteria | Acceptance criteria | Estimate (User Story Points) | comment
EPIC 1 | Matching system | US1-1 | As a patient | Given the patient is logged in. When the patient select a physician to consult with Then notify the physician about the new request And ensure the request is recorded and processed correctly | Given | 13 | fetch
|  |  | I want to select a physician |  | When
|  |  | so that I can consult a physician |  | Then
|  | US1-2 | As a physician | Given the physician is loggen in. And the patient requested a consultation with the physician When the physician accepts the consultation request Then update the request status And notify the patient that their request is accepted |  | 13 | fetch
|  |  | I want to accept patients' request to consult with me |  |  |  | notify
so that I can give consultations to patients
|  | US1-3 | As a physician | Given the patient requested a consultation with the physician When the physician rejects the consultation request Then update the request status And notify the patient that their request is rejected. |  | 13
I want to decline patients' requests
so that the patients can send requests to another physician
|  | US1-4 | As a patient | Given a list of physicians And sorting criteria from the patient When the patient wants to sort the list Then ensure that the list is sorted correctly according to the relevant factors |  | 3
I want to be able to sort the physician’s list by the relevant factors
so that I can select the best physicians for me
|  | US1-5 | As a patient | Given every physician's profile has a valid working hour When the patient select a physician Then display the physicians' working hours |  | 2
I want to see the physician’s working hours
so that I can select the best physicians that are available
|  | US1-6 | As a patient | Given the patient's primary symptoms, physicians’ names, stationed clinics, or specialties. When the patient wants to find the physician. Then display a physician's list based on patient's primary symptoms, physicians’ names, stationed clinics, or specialties. |  | 5
I want to search physicians
so that I can select appropriate physicians
|  | US1-7 | As a patient | Given the patient has existing request(s) When the patient wants to view their matching status Then display the matching status |  | 3
I want to see the matching status
so that I can know where my request state is in
|  | US1-8 | As a patient | Given the patient has existing request(s) When the patient wants to cancel the request Then update the request status accordingly |  | 2
I want to cancel the request
so that I am free to change my plan
EPIC 2 | Registration and Login system | US2-1 | As a patient | Given the patient never has registered to the system When the patient wants to register to the system Then display the registration form And ensure correct data is recorded |  | 8
I want to register to the system
so that I can consult a physician
|  | US2-2 | As a physician | Given the physician never has registered to the system When the physician wants to register to the system Then display the registration form And ensure correct data is recorded |  | 8
I want to register to the system
so that I can give consultations to patients
|  | US2-3 | As a patient | Given the credit/debit card information is valid When the patient provides the credit/debit information. Then record the information And ensure the security of the card information |  | 3
I want to provide a credit/debit card information
so that I can pay service fees
|  | US2-4 | As a physician | Given the physician's medical license, specialties and working hour When the physician wants to register physician's medical license, specialties and working hour to the system Then record the provided medical license, specialties and working hour |  | 3
I want to provide my Medical License, specialties and working hour
so that I will be reliable and credible
|  | US2-5 | As a patient | Given the patient is logged in into the system When the patient edit their profile Then ensure edited profile is recorded | Given | 5 | new design
|  |  | I want to edit my profile |  | When
|  |  | So that my profile is up-to-date |  | Then
|  | US2-6 | As a physician | Given the physician is logged in into the system When the physician edit their profile Then ensure edited profile is recorded |  | 5 | new design
I want to edit my profile
So that my profile is up-to-date
|  | US2-7 | As a patient | Given the patient is not logged in into the system When the patient log in to the system Then display the log in form and authenticate the user |  | 21 | auth
I want to log in to the system
so that I can consult with a physician
|  | US2-8 | As an admin | Given the physician profile When the admin wants to verify the physician profile Then display the physician's profile And allow the admin to accept or deny the profile And notify that physician about the verifying status. |  | 21
I want to verify the physicians' profiles
so that I can ensure the credibility of the system
EPIC 3 | Video call system | US3-1 | As a patient | Given the physician accept matching request And the patient's device can use video call function And the physician's device can use video call function When the patient send a video call request to the physicain Then ensure the request is sent to the physician And ensure the patient is informed about the request status |  | 8
I want to request a video call to a physician
so that I can ask about my illness directly
|  | US3-2 | As a physician | Given the physician accept matching request And the patient's device can use video call function And the physician's device can use video call function When the physician send a video call request to the patient Then ensure the request is sent to the patient And ensure the physician is informed about the request status |  | 8
I want to request a video call to a patient
so that I can give advice to him/her about his/her illness
|  | US3-3 | As a patient | Given the patient receive a video call request from the physician When the patient accept the video call request Then trigger video call function on both patient's and physician's device And ensure both patient and physician can turn camera on/off And ensure both patient and physician can turn microphone on/off |  | 55 | video call
I want to accept video call requests from physicians
so that I can ask about my illness directly
|  | US3-4 | As a physician | Given the physician receive a video call request from the patient When the physician accept the video call request Then trigger video call function on both patient's and physician's device And ensure both patient and physician can turn camera on/off And ensure both patient and physician can turn microphone on/off |  | 55
I want to accept video call requests from patients
so that I can give advice to them about their illness
|  | US3-5 | As a patient | Given the patient receive a video call request from the physician When the patient reject the video call request Then send a notification to the physician that the patient reject the request And ensure the physician can send request again And ensure matching status is still matched |  | 5
I want to reject video call requests from physicians
so that the physicians could not see me if I don't want them to
|  | US3-6 | As a physician | Given the physician receive a video call request from the patient When the physician reject the video call request Then send a notification to the patient that the physician reject the request And ensure the patient can send request again And ensure matching status is still matched |  | 5
I want to reject video call requests from patients
so that the patients could not see me in person if I don't want them to
EPIC 4 | Payment system | US4-1 | As a patient | Given the credit/debit card is added to the system And the credit/debit card is valid (not expired) And there is a balance in the account When the patient send payment request Then deduct the balance in the account using payment gateway |  | 34 | payment gateway
I want to make a payment via credit/debit card
so that I don't have to pay with cash, for safety during COVID-19 pandemic
|  | US4-2 | As a physician | Given physician's payment method is valid When the physician requests to withdraw the consultation fee Then the system transfer the remaining fee of this physician's account to the given payment method |  | 21
I want to withdraw the consultataion fee
so that I can receive the money
|  | US4-3 | As a patient | Given the patient payment record is exist When the patient want to see thier records Then display the patient payment record |  | 2
I want to see my payment record
so that I can keep tracking my transaction
|  | US4-4 | As a patient | Given the credit/debit card is valid When the patient add the credit/debit card Then the credit/debit card information is displayed on the payment screen |  | 3
I want to add new credit/debit card to the system
so that I can change my payment to the new card
|  | US4-5 | As a patient | Given list of patient credit/debit cards When the patient want to make a payment Or manage the cards (add/delete) Then displays every patient credit/debit cards as a list |  | 2
I want the system to remember all cards that I have added
so that I don't have to bring my card with me everytime I want to make a payment
|  | US4-6 | As a physician | Given the recent physician bank account number When the physician requests to withdraw the consultation fee Then displays the physician bank account number |  | 2
I want the system to remember my bank account
so that I don't have to add my payment method everytime I want to withdraw the consultation fee
EPIC 5 | Rating system | US5-1 | As a patient | Given that the rating is valid When the patient add rating for the physician Then display the rating that the patient has given on screen And record the rating to the physician's rating record |  | 3
I want to rating the physician
so that I can feedback and share my feeling about service
|  | US5-2 | As a patient | Given that the comment is valid When the patient add comment for the physician Then display the comment that the patient has given on screen And record the comment to the physician's comment record |  | 3
I want to comment the physician
so that I can feedback and share my feeling about service
|  | US5-3 | As a patient | Given the physician's rating and comment record is exist When the patients requests to see rating and comment of the physician Then display rating and comment of the physician on screeen |  | 3
I want to see rating and comment of physician
so that I can use it for choosing physicians
|  | US5-4 | As a physician | Given the physician's rating and comment record is exist When the physician requests to see rating and comment of themselves Then display rating and comment of the physician on screeen |  | 3
I want to see my rating and comment
so that I can monitor patient satisfaction and improve my service
|  | US5-5 | As a patient | Given the physician's consultation record is exist When the patient requests to see the total number of patients that have consulted with the physician Then display the total number of patients that have consulted with the physician on screen |  | 2
I want to see the total number of patients that have consulted with the physician
so that I can use it for choosing physicians
|  | US5-6 | As a physician | Given the physician's consultation record is exist When the physician requests to see the total number of patients that have consulted with them Then display the total number of patients that have consulted with the physician on screen |  | 2
I want to see the total number of patients that have consulted with me
so that I can keep it to be my statistic
EPIC 6 | Chatting system | US6-1 | As a patient | Given the physician accepted matching request When the patient send text messages to the physician Then ensure the system send notifications to the physician And the messages are displayed on the physician's device |  | 55 | real time msg
I want to send text messages to physicians
so that I can communicate with the physicians
|  | US6-2 | As a physician | Given the physician accepted matching request When the physician send text messages to the patient Then ensure the system send notifications to the patient And the messages are displayed on the patient's device |  | 55
I want to send text messages to patients
so that I can communicate with the patients
|  | US6-3 | As a patient | Given the system store messages in the databases When the patient enter the chatting room Then ensure the system show all messages in the chatting room ordered by sending time |  | 8
I want to see past messages in my chats
so that I can look back at my consultations
|  | US6-4 | As a physician | Given the system store messages in the databases When the physician enter the chatting room Then ensure the system show all messages in the chatting room ordered by sending time |  | 8
I want to see past messages in my chats
so that I can look back at consultations I have given
|  | US6-5 | As a patient | Given the physician accepted mathcing request When the patient send images to the physician Then ensure the system send notification to the physician And the images are displayed on the physician's device |  | 13
I want to send images to physicians
so that I can communicate with the physicians
|  | US6-6 | As a physician | Given the physician accepted mathcing request When the physician send images to the patient Then ensure the system send notification to the patient And the images are displayed on the patient's device |  | 13
I want to send images to patients
so that I can communicate with the patients
|  | US6-7 | As a patient | Given the patient has an active chatroom And the chatroom is unmute When the patient receive new messages in chat Then ensure the patient is notified visually and auditorily |  | 13 | real time noti
I want to receive chat notifications
So that I know I have new messages
|  | US6-8 | As a physician | Given the physician has an active chatroom And the chatroom is unmute When the physician receive new messages in chat Then ensure the physician is notified visually and auditorily |  | 13
I want to receive chat notifications
So that I know I have new messages
|  | US6-9 | As a patient | Given the patient has an active chatroom When the patient toggle the mute/unmute chat notifications setting Then ensure the chat notifications are mute/unmute as toggled |  | 2 | set 1 value
I want to mute/unmute my chat notifications
so that I can temporarily avoid disturbance
|  | US6-10 | As a physician | Given the physician has an active chatroom When the physician toggle the mute/unmute chat notifications setting Then ensure the chat notifications are mute/unmute as toggled |  | 2
I want to mute/unmute my chat notifications
so that I can temporarily avoid disturbance
EPIC 7 | Appointment System | US7-1 | As a physician | Given that a patient has chosen the physician. When the physician finish creating an appointment with that patient. Then the system shall send that appointment to the patient. |  | 8
I want to send appointments to patients
so that I can call patient to the hospital
|  | US7-2 | As a physician | Given there's an appointment. When the physician cancel an appointment with reasons given. Then the system shall delete that appointment from both patient and physician list. And notify the patient about the deletion and its reason. |  | 3
I want to cancel the appointment
so that I can delete the unnecessary appointment
|  | US7-3 | As a patient | Given there's an appointment. When the patient cancel an appointment with reasons given. Then the system shall delete that appointment from both patient and physician list. And notify the patient about the deletion and its reason. |  | 3
I want to cancel the appointment
so that I can delete the unnecessary appointment
|  | US7-4 | As a physician | Given there's an appointment. When the physician finish editing and rescheduling the appointment. Then the system shall send that change request to the patient for an approval. |  | 8
I want to edit and reschedule the appointment by sending a request to the patient
so that the appointment will have appropriate information
|  | US7-5 | As a patient | Given there's an appointment. When the patient finish editing and rescheduling the appointment. Then the system shall send that change request to the physician for an approval. |  | 8
I want to edit and reschedule the appointment by sending a request to the physician
so that the appointment will have appropriate information
|  | US7-6 | As a physician | Given the physician is logged in. When the physician requests to check the appointment time. Then the system shall display the physician's appointment timetable. |  | 3
I want to inspect my appointment timetable
so that I can check the appointment time
|  | US7-7 | As a patient | Given the patient is logged in. When the patient requests to check the appointment time and place. Then the system shall display the patient's appointment list. |  | 3
I want to view the appointment list
so that I can manage my time and go to hospital at the reserved time
Note on C3: เลือกปรึกษากับแพทย์ท่านนี้ -Raviporn Akekunanon
Note on C12: Sort icon -Raviporn Akekunanon
Note on C15: Physician search > ดูเพิ่มเติม -Raviporn Akekunanon
Note on C18: Search in hamburger menu -Raviporn Akekunanon
Note on C21: consultation page in hamburger menu -Raviporn Akekunanon
Note on C24: Consultation > Cancel button -Raviporn Akekunanon
Note on C27: Register button -Raviporn Akekunanon
Note on C30: Register button -Raviporn Akekunanon
Note on C33: add credit card in hamburger menu -Raviporn Akekunanon

## Sprint1
| EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
Sprint1 | EPIC1 | Matching system | US1-1 | As a patient I want to select a physician so that I can consult a physician | Setup backend server & architecture | Atiwat | Tarm | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Setup Database (mongodb) | Tarm | Atiwat | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Setup React, folder structures, .gitignore, prettier, and React router | Kittipong | Kanokpich | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Setup tailwindcss and design system | Kittipong | Jirawat | Done | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design model schema | Tarm | Thitaree | Done | 8 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement API for fetching physician data | Tarm | Atiwat | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement API for matching requests | Thitaree | Atiwat | Done | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement API for notification | Thitaree | Atiwat | Done | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician data card (Group 1 in figma) | Jirawat | Nopdanai | Done | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement comment card (Used in Selection frame) | Nopdanai | Raviporn | Done | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement notification button component + notification card and components (For physician) | Raviporn | Nopdanai | Done | 5 | 5 | 5 | 4 | 3.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement other buttons (The button that uses everywhere) | Kanokpich | Raviporn | Done | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement patient's search page (So that, user can pick physician) | Kittipong | Raviporn | Done | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician selection page (So that, user can pick physician) | Nopdanai | Kanokpich | Done | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement after selection page | Jirawat | Raviporn | Done | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician page (Only to include notification button) | Kanokpich | Kittipong | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-2 | As a physician I want to accept patients' request to consult with me so that I can give consultations to patients | Implement patient acceptance card (So that physician can accept and reject the patient) | Jirawat | Nopdanai | Done | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Finishing touch on implementing the physician page | Kanokpich | Kittipong | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
|  |  | AND |  | Implement patient detail page (Selection in Physician's page figma) | Jirawat | Nopdanai | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | US1-3 | As a physician I want to decline patients' requests so that the patients can send requests to another physician | Implement an update-request endpoint | Atiwat | Thitaree | Done | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-4 | As a patient I want to be able to sort the physician’s list by the relevant factors so that I can select the best physicians for me | Implement sorted icon and sorted criteria card on patient's search page | Jirawat | Kanokpich | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1.5 | 1.5 | 1.5 | 1 | 1 | 0.5 | 0 | 0
[5 empty] | Implement http method for sorted data + show them on the page | Kittipong | Nopdanai | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
[5 empty] | modify fetching-physician-data endpoint to be able to return sorted data | Atiwat | Tarm | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-5 | As a patient I want to see the physician’s working hours so that I can select the best physicians that are available | Design physician information page (including working hours) | Raviporn | Kanokpich | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician information page (including working hours) | Kanokpich | Nopdanai | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement a get-working-hour endpoint | Thitaree | Atiwat | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-6 | As a patient I want to search physicians so that I can select appropriate physicians | Implement search box component | Kanokpich | Jirawat | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement http method for requesting search data, retrieve itm and show it on the display | Kittipong | Nopdanai | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0
[5 empty] | Implement search-physician endpoint | Atiwat | Tarm | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-7 | As a patient I want to see the matching status so that I can know where my request state is in | Design consultation page (Primarily, need to show matching status) | Kanokpich | Raviporn | Done | 2 | 2 | 2 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design matching status card (To include physician's name, status, accept, and reject) | Raviporn | Thitaree | Done | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement consultation page | Jirawat | Kanokpich | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement menu (hamburger) bar | Raviporn | Kittipong | Done | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement get-matching-status endpoint | Tarm | Thitaree | Done | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US1-8 | As a patient I want to cancel the request so that I am free to change my plan | Implement http method for canceling the matching | Kanokpich | Jirawat | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0
[5 empty] | add cancel request in update-request endpoint | Atiwat | Thitaree | Done | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIC2 | Registration and Login system | US2-1 | As a patient I want to register to the system so that I can consult a physician | Implement patient-register endpoint | Atiwat | Thitaree | Done | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement custom textbox | Kittipong | Raviporn | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement patient's registration page | Jirawat | Nopdanai | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
|  |  | US2-2 | As a physician I want to register to the system so that I can give consultations to patients | Implement physician-register endpoint | Thitaree | Tarm | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician registration page | Kanokpich | Jirawat | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
|  |  | US2-3 | As a patient I want to provide a credit/debit card information so that I can pay service fees | Design card addition page | Raviporn | Thitaree | Done | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement card addition page | Raviporn | Jirawat | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 | 0 | 0 | 0
[5 empty] | Design credit card schema | Thitaree | Atiwat | Done | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement add-credit-card endpoint | Atiwat | Tarm | Done | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-4 | As a physician I want to provide my Medical License, specialties and working hour so that I will be reliable and credible | Implement physician registration page (Page 2-3) | Raviporn | Kittipong | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
[5 empty] | modify physician-register endpoint | Atiwat | Thitaree | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
[8 empty] | Todo | ยังไม่ select มาทำ
[8 empty] | Develop | กำลัง develop (design and code)
[8 empty] | Test | กำลัง test
[8 empty] | Done | ทำเสร็จ
[5 empty] | Total |  |  |  | 112 | 97 | 91 | 83 | 82.5 | 76 | 61 | 49 | 42 | 29.5 | 26 | 17.5 | 7 | 2.5 | 0 | 0
[8 empty] | Goal | 112
Sprint Goal
Deliver a whole of matching system and some part of registration system
[6 empty] | sum hour | count task
[5 empty] | Raviporn | 14 | 13
[5 empty] | Kittipong | 13.5 | 10
[5 empty] | Jirawat | 13.5 | 12
[5 empty] | Nopdanai | 16 | 10
[5 empty] | Kanokpich | 15 | 13
[5 empty] | Thitaree | 13.5 | 13
[5 empty] | Atiwat | 13.5 | 14
[5 empty] | Tarm | 13 | 9
Note on K3: overestimate
Note on K4: overestimate
Note on M13: หาวันนัดไม่ได้
Note on N13: ทำตั้งนาน เหลือเยอะเท่าเดิม max sad
Note on F27: This also means, you have to update the physician information in a way that it includes "ดูรายละเอียดเพิ่มเติม" button that redirects user to the physician's information page. -Kittipong Deevee
Note on E29: For frontend, US1-6 we kinda need to work together closely. -Kittipong Deevee
Note on P35: overestimate
Note on J40: This might also be more difficult than expected, as the text box has to be available for map coordination picking (for US2-4) also. -Kittipong Deevee
Note on J41: This might be more difficult than expected, as data validation (might be) required before submitting the information. -Kittipong Deevee

## Sprint2
e | [9 empty] | T | F | S | S | M | T | W | T | F | S | S | M | T | W
| EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Sprint Review
Sprint2 | EPIC2 | Registration and Login system | US2-5 | As a patient I want to edit my profile So that my profile is up-to-date | Setup AWS S3 service | Atiwat | Tarm | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement update patient endpoint (include set profile image) | Atiwat | Tarm | Done | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design patient account page (including profile and edit button) | Raviporn | Kanokpich | Done | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement update patient page + all api requests needed to update the information | Jirawat | Raviporn | Done | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-6 | As a physician I want to edit my profile So that my profile is up-to-date | Implement update physician endpoint (include set profile image) | Thitaree | Tarm | Done | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design physician account page (including profile and edit button) | Raviporn | Nopdanai | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement update physician page + all api requests needed to update the information | Jirawat | Raviporn | Done | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-7 | As a patient I want to log in to the system so that I can consult with a physician | Implement jwt token and passport service | Atiwat | Tarm | Done | 7 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician login (authentication & authorization service) | Atiwat | Tarm | Done | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement patient login (authentication & authorization service) | Thitaree | Tarm | Done | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AND |  | Design login page | Raviporn | Kanokpich | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-9 | As a physician I want to log in to the system so that I give consultations to patients | Implement routes management on authentication states and default endpoints | Kittipong | Kanokpich | Done | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement login page | Kanokpich | Nopdanai | Done | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement all api requests needed to perform login. | Kittipong | Kanokpich | Done | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement cookies to store jwt token from backend. | Kittipong | Nopdanai | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Session management | Nopdanai | Kanokpich | Done | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement logout button | Raviporn | Nopdanai | Done | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | hamburger bar | Raviporn | Kanokpich | Done | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US2-8 | As an admin I want to verify the physicians' profiles so that I can ensure the credibility of the system | Create admin model | Thitaree | Tarm | Done | 1 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement admin login (authentication & authorization service) | Thitaree | Tarm | Done | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design admin's acceptance page | Raviporn | Kanokpich | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement physician register request component (including accept and decline button) | Raviporn | Jirawat | Done | 3 | 3 | 3 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement admin page | Raviporn | Jirawat | Done | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIC6 | Chatting System | US6-1 | As a patient I want to send text messages to physicians so that I can communicate with the physicians | Design chat page | Raviporn | Kanokpich | Done | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AND |  | Implement nestjs web socket | Atiwat | Thitaree | Done | 6 | 6 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-2 | As a physician I want to send text messages to patients so that I can communicate with the patients | Implement ChatMessage model | Atiwat | Thitaree | Done | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AND |  | Implement chat bubble component | Jirawat | Nopdanai | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-3 | As a patient I want to see past messages in my chats so that I can look back at my consultations | Implement text box input with attachment (but not the microphone, there's no voice text in the requirement) | Jirawat | Nopdanai | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AND |  | Implement send button | Jirawat | Kittipong | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-4 | As a physician I want to see past messages in my chats so that I can look back at consultations I have given | Implement chat page (Assemble) | Kittipong | Jirawat | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement chat mechanism (socket link, or some sort) | Kittipong | Nopdanai | Done | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 6 | 4 | 2 | 0 | 0 | 0
[5 empty] | Managing chat history. (On backend?, Socket?) | Nopdanai | Jirawat | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement get ChatMessage endpoint | Thitaree | Atiwat | Done | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-5 | As a patient I want to send images to physicians so that I can communicate with the physicians | Implement image sending mechanism to textbox and send message | Raviporn | Kanokpich | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
|  |  | AND |  | implemt upload image in ChatMessage module | Thitaree | Tarm | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-6 | As a physician I want to send images to patients so that I can communicate with the patients
|  |  | US6-7 | As a patient I want to receive chat notifications So that I know I have new messages | Implement notification listener | Raviporn | Kanokpich | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
|  |  | AND |  | add chat notification in notification module | Atiwat | Thitaree | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-8 | As a physician I want to receive chat notifications So that I know I have new messages
|  |  | US6-9 | As a patient I want to mute/unmute my chat notifications so that I can temporarily avoid disturbance | Implement mute/unmute button (to toggle status of chat notification) | Raviporn | Kanokpich | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
|  |  | AND |  | Implement set mute/unmute status in notification module | Thitaree | Atiwat | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US6-10 | As a physician I want to mute/unmute my chat notifications so that I can temporarily avoid disturbance
[8 empty] | Todo | ยังไม่ select มาทำ
[8 empty] | Develop | กำลัง develop (design and code)
[8 empty] | Test | กำลัง test
[8 empty] | Done | ทำเสร็จ
[5 empty] | Total |  |  |  | 114 | 107.5 | 91 | 76 | 68.5 | 57 | 50 | 44 | 30 | 19 | 13 | 9 | 7 | 2 | 0 | 0
[10 empty] | 6.5 | 16.5 | 15 | 7.5 | 11.5 | 7 | 6 | 14 | 11 | 6 | 4 | 2 | 5 | 2 | 0
[8 empty] | Goal | 112
Sprint Goal
Deliver a complete registration system and chatting system
[6 empty] | sum hour | count task
[5 empty] | Raviporn | 15.5 | 14
[5 empty] | Kittipong | 13.5 | 6
[5 empty] | Jirawat | 15 | 9
[5 empty] | Nopdanai | 16.5 | 9
[5 empty] | Kanokpich | 14.5 | 12
[5 empty] | Thitaree | 12 | 10
[5 empty] | Atiwat | 14 | 9
[5 empty] | Tarm | 13 | 9
Note on F8: ไปลอกหน้าพี่สุชาติ เพิ่ม add work hours ด้วย
Note on M24: Wait for backend api
Note on M25: Wait for backend api
Note on F29: - รู้ว่าเป็นข้อความของใคร - สามารถเป็นรูปได้ -Raviporn Akekunanon
Note on F30: - text box with full function - attachment selection only (cannot send) -Raviporn Akekunanon
Note on F31: send text message only (for now), image later -Raviporn Akekunanon
Note on F33: อันนี้ช่วยกันหมด 3 คน -Kittipong Deevee
Note on F56: เผื่อเวลาให้ผม PR ด้วย -Kittipong Deevee

## Sprint3
[10 empty] | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30
| EPIC ID | EPIC Name | User Story ID | User Story | Task | Volunteer |  | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Sprint Review
Sprint 3 | EPIC3 | Video call system | US3-1 | As a patient I want to request a video call to a physician so that I can ask about my illness directly | (chat gateway) implement subscribe message "call user" | Atiwat | Thitaree | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AND | Study about video call system along with libraries, dependecies, and network conceptes needed to make one. | Atiwat | Thitaree | Done | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US3-2 | As a physician I want to request a video call to a patient so that I can give advice to him/her about his/her illness | Design a fixed banner for interlocutor to accept or reject a video call request. | Raviporn | Kittipong | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create a banner for interlocutor to accept or reject a video call request. | Nopdanai | Kanokpich | Done | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement a video call request / acceptance / rejection procedure. | Nopdanai | Kanokpich | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US3-3 | As a patient I want to accept video call requests from physicians so that I can ask about my illness directly | (chat gateway) implement subscribe message "answer call" | Atiwat | Thitaree | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | AND | Design a video call page. | Raviporn | Kanokpich | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US3-4 | As a physician I want to accept video call requests from patients so that I can give advice to them about their illness | Create a layout for video call page. | Nopdanai | Jirawat | Develop | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 2 | 2 | 3 | 2 | 2 | 1 | 1 | 0 | 0
|  |  |  | AND | Implement a video call system. | Kittipong | Jirawat | Develop | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 13 | 10 | 6 | 3 | 5 | 4 | 3 | 2 | 1 | 0 | 0
|  |  | US3-5 | As a patient I want to reject video call requests from physicians so that the physicians could not see me if I don't want them to | bar: 2022-03-15 to 2022-03-18
AND | bar: 2022-03-15 to 2022-03-18
|  |  | US3-6 | As a physician I want to reject video call requests from patients so that the patients could not see me in person if I don't want them to | bar: 2022-03-15 to 2022-03-18
| EPIC4 | Payment system | US4-1 | As a patient I want to make a payment via credit/debit card so that I don't have to pay with cash, for safety during COVID-19 pandemic | Design transaction model | Atiwat | Tarm | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | implement omise charge with card (also deduct fee) | Atiwat | Thitaree | Done | 12 | 10 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design page between /SelectPhysician and /ConfirmedPhysicianSelection for patient to make a payment | Raviporn | Nopdanai | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create page between /SelectPhysician and /ConfirmedPhysicianSelection for patient to make a payment | Jirawat | Raviporn | Done | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement payment transfer procedure | Jirawat | Raviporn | Done | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US4-2 | As a physician I want to withdraw the consultataion fee so that I can receive the money | Design transfer model | Atiwat | Tarm | Done | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | implement omise transfer | Atiwat | Tarm | Done | 12 | 12 | 12 | 10 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design withdrawal page | Raviporn | Nopdanai | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create withdrawal page | Nopdanai | Raviporn | Done | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement withdraw procedure | Nopdanai | Raviporn | Done | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US4-3 | As a patient I want to see my payment record so that I can keep tracking my transaction | implement get transaction endpoint | Thitaree | Tarm | Done | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create payment record page + fill information with data from an API. | Kittipong | Kanokpich | Done | 6 | 6 | 6 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US4-4 | As a patient I want to add new credit/debit card to the system so that I can change my payment to the new card | Create a page to show all credit/debit cards in the system, along with the button to add card. | Kanokpich | Kittipong | Done | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US4-5 | As a patient I want the system to remember all cards that I have added so that I don't have to bring my card with me everytime I want to make a payment | bar: 2022-03-15 to 2022-03-18
|  |  | US4-6 | As a physician I want the system to remember my bank account so that I don't have to add my payment method everytime I want to withdraw the consultation fee | Create a bank account information page for physician + fill information with data from an API. | Kanokpich | Jirawat | Done | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EPIC5 | Rating system | US5-1 | As a patient I want to rating the physician so that I can feedback and share my feeling about service | Design rating model | Thitaree | Tarm | Done | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | AND | implement create rating endpoint (also update physician's rating field) | Thitaree | Tarm | Done | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US5-2 | As a patient I want to comment the physician so that I can feedback and share my feeling about service | Create/Alter pages as follow - Cards alteration in AllChat page for physician to include "complete" button (indicating this matchin is done). - Create a page for patient that assembles all physician waited for the review. (With necessary cards) - Create a page for patient to review a physician. | Raviporn | Kanokpich | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Alter cards in AllChat page for physician to include "complete" button (indicating this matchin is done) | Kittipong | Jirawat | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create a page for patient that assembles all physician waiting for the review. (With necessary cards) | Kanokpich | Raviporn | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Create a page for patient to review a physician. | Nopdanai | Raviporn | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US5-3 | As a patient I want to see rating and comment of physician so that I can use it for choosing physicians | modify update request status (add complete status and increase physician's total patient when complete) | Thitaree | Tarm | Done | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AND | bar: 2022-03-15 to 2022-03-18
|  |  | US5-5 | As a patient I want to see the total number of patients that have consulted with the physician so that I can use it for choosing physicians | Alter cards in /SearchPhysician to include physician rating and number of patients consulted with this physician. | Kittipong | Jirawat | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | US5-4 | As a physician I want to see my rating and comment so that I can monitor patient satisfaction and improve my service | implent get own rating endpoint | Thitaree | Tarm | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AND | bar: 2022-03-15 to 2022-03-18
|  |  | US5-6 | As a physician I want to see the total number of patients that have consulted with me so that I can keep it to be my statistic | Alter the physician information page to include physician rating and number of patients consulted with this physician. | Kittipong | Jirawat | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
0
[8 empty] | Todo | ยังไม่ select มาทำ
[8 empty] | Develop | กำลัง develop (design and code)
[8 empty] | Test | กำลัง test
[8 empty] | Done | ทำเสร็จ
[5 empty] | Total |  |  |  | 165 | 159 | 152 | 121 | 105 | 97 | 91 | 79 | 66 | 57 | 48 | 22 | 12 | 14 | 7 | 5 | 3 | 2 | 0 | 0
Sprint Goal
Deliver the complete video call system, the complete payment system and the complete rating system
[6 empty] | sum hour | count task
[5 empty] | Raviporn | 19.5 | 11
[5 empty] | Kittipong | 19 | 7
[5 empty] | Jirawat | 24.5 | 8
[5 empty] | Nopdanai | 16.5 | 8
[5 empty] | Kanokpich | 19.5 | 8
[5 empty] | Thitaree | 23 | 9
[5 empty] | Atiwat | 22.5 | 7
[5 empty] | Tarm | 20.5 | 8
Note on E12: backend น่าจะไม่ต้องทำอะไร -Atiwat Deepo Will be done concurrently with US3-1 to 3-4 -Kittipong Deevee
Note on E14: backend น่าจะไม่ต้องทำอะไร -Atiwat Deepo
Note on E27: backend ทำเสร็จแล้วใน sprint ก่อนหน้า -Atiwat Deepo
Note on E28: backend ทำเสร็จแล้วใน sprint ก่อนหน้า -Atiwat Deepo
Note on E29: backend ทำเสร็จแล้วใน sprint ก่อนหน้า -Atiwat Deepo
Note on E38: backend ใช้ get physician by id ดูข้อมูลได้ -Atiwat Deepo
Note on E41: backend ใช้ get physician profile ดูข้อมูลได้ -Atiwat Deepo